EXECUTIVE SUMMARY

Employee Engagement Survey — Results, Action Plan & Progress

# 1. Survey Snapshot

We ran the 2025 employee engagement survey in September, shared full results back with employees by December, and released the Action Plan enterprise-wide in March 2026, built with Voice Team input at every step. Overall engagement came in at 62%, though it varied by site:

| Site | Participation | Engagement | Lowest Scoring Item | Highest Scoring Item |
| --- | --- | --- | --- | --- |
| Enterprise Overall | 62.8% | 62% | Action (35%) | Learning & Development (59%) |
| NJ — Livingston | 73.0% | 53% | Leadership / Innovation (tied, 40%) | Social Connection (56%) |
| TX — Point Comfort | 62.6% | 63% | Action (33%) | Compensation & Rewards (56%) |
| LA — Baton Rouge | 52.3% | 67% | Action (31%) | Company Confidence (61%) |

Action stands out as the clearest priority in the plan. It's the lowest-scoring item enterprise-wide and at every individual site, including a 31% score at LA, the single lowest score anywhere in the survey, even though LA also posted the highest overall engagement. Participation tells its own story too: NJ had the highest response rate of any site (73%) but the lowest engagement score (53%), a reminder that showing up to take the survey and feeling good about the workplace are two different things.

# 2. Key Findings by Theme

The Action Plan is built around eight themes. Action, Feedback & Recognition, and Leadership scored lowest enterprise-wide:

| Theme | Score | What it means |
| --- | --- | --- |
| Action | 35% | Lowest enterprise-wide theme: employees have limited confidence that survey feedback leads to real follow-through. |
| Feedback & Recognition | 43% | Only 35% feel the right people are recognized; recognition is seen as inconsistent across sites and departments. |
| Collaboration & Communication | 49% | Employees at all three sites report feeling disconnected from how decisions get made. |
| Leadership | 45% | Below 50% at every single site — the most consistent gap in the survey. |
| Service & Quality Focus | 45% | Employees feel quality standards and performance aren't consistently recognized. |
| Innovation | 50% | Employees want to contribute ideas but see limited follow-through on them. |
| Company Confidence | 55% | Moderate confidence in the company's direction and long-term stability. |
| Learning & Development | 59% | Relative strength, but employees still want clearer growth paths. |

# 3. The Action Plan — 8 Focus Areas

Those findings turned into five enterprise-wide focus areas and three site-specific ones (one per site), each with two concrete initiatives:

| # | Level | Focus Area | Key Initiatives | Priority |
| --- | --- | --- | --- | --- |
| 1 | Enterprise | Execution Discipline & Follow-Through Visibility | Deploy Enterprise Action Tracker; Standardize "You Said / We Did" template | High |
| 2 | Enterprise | Recognition Consistency & Leadership Accountability | Launch Recognition / Spot Award platform; Activate site-wide recognition visibility | High |
| 3 | Enterprise | Enterprise Goal & Decision Transparency | Communicate all policy changes; Launch quarterly leadership update | High |
| 4 | Enterprise | Structured Leadership Development Pipeline | Launch 12-week leadership program; Introduce monetary incentives | High |
| 5 | Enterprise | Enterprise Innovation & Confidence Roadmap | Launch innovation email inbox; Align succession planning | High |
| 6 | NJ Livingston | Leadership Visibility, Innovation & Employee Experience | Monthly leadership listening sessions; Pilot rotational program | High/Med |
| 7 | TX Point Comfort | Leadership Accountability, Performance Clarity & Pay Transparency | TX leadership expectations framework; Texas pay FAQ | High/Med |
| 8 | LA Baton Rouge | Manager Enablement & Accountability Reinforcement | Site-wide town halls & peer reviews; Personnel management & conflict resolution training | High |

# 4. One Year of Progress

Six months from the release of the action plan, 13 of our 16 initiatives across all 8 focus areas are complete or underway, and the remaining 3 are queued up next. The whole plan is already delivered, in motion, or scheduled to launch:

| Area | Initiative | Progress (%) | Status |
| --- | --- | --- | --- |
| 1 — Enterprise | Deploy Enterprise Action Tracker | 100% | Complete |
|  | Standardize "You Said / We Did" template | 60% | In Progress |
| 2 — Enterprise | Launch Recognition / Spot Award platform | 100% | Complete |
|  | Activate site-wide recognition visibility | 100% | Complete |
| 3 — Enterprise | Communicate all policy changes | 100% | Complete |
|  | Launch quarterly leadership update | 100% | Complete |
| 4 — Enterprise | Launch 12-week leadership program | 100% | Complete |
|  | Introduce monetary incentives | 30% | In Progress |
| 5 — Enterprise | Launch innovation email inbox | 0% | Up Next |
|  | Align succession planning | 35% | In Progress |
| 6 — NJ Livingston | Monthly leadership listening sessions | 40% | In Progress |
|  | Pilot rotational program | 0% | Up Next |
| 7 — TX Point Comfort | TX leadership expectations framework | 66% | In Progress |
|  | Texas pay FAQ | 66% | In Progress |
| 8 — LA Baton Rouge | Site-wide town halls & peer reviews | 0% | Up Next |
|  | Personnel management & conflict resolution training | 75% | In Progress |

## Where things stand

- Six initiatives are completed: the Enterprise Action Tracker, the Recognition & Spot Award platform, site-wide recognition visibility, both pieces of Enterprise Goal & Decision Transparency, and the 12-week Leadership Program.

- Seven more are moving fast: both TX initiatives are at 66%, LA's training initiative is at 75%.

- Three more, the innovation inbox, NJ's rotational program pilot, and LA's town halls & peer reviews, are queued up next.

- That progress is spread across every site, not concentrated in one place. For the full breakdown, initiative by initiative, the Action Plan Tracker has the current numbers.

# 5. Bottom Line

Within the first 6 months, more than 80% of the Action Plan is delivered or in motion, and it's spread across every site, not just the easy wins. The Recognition platform is live, the first Leadership Program cohort has graduated, and this tracker is proof that what got committed to in March is actually getting done by September. There's more happening than fits on this page. Check the live Action Plan Tracker for the full, current picture.

# 6. Beyond the Numbers

Percentages and status bars are one way to look at the year. Here's the other way: this started as a promise that employee feedback wouldn't just disappear into a report. Since results went out in December 2025, that's turned into a Recognition & Spot Award platform running company-wide, a first class of leaders who've finished the 12-week Leadership Program, a quarterly leadership update that's actually happening, and this tracker, which was itself one of the first things we promised to build.

There's more in the works than we can list here. What matters is that this hasn't been a plan we published once and moved on from. It's still moving. For the current status of every initiative, the tracker is the place to look.

# 7. Looking Ahead — The 2027 Survey

That's also why this is the right time to open the next chapter. The 2027 Employee Engagement Survey runs October 5 to 30, our second year running it. This will be our first real year-over-year comparison, a chance to see whether the last twelve months actually moved the numbers that mattered most in 2025, especially Action and Leadership. It's also the next chance to shape what comes after this plan, the same way last year's feedback shaped this one.

We're treating the first cycle in 2025 as our benchmark. In 2026, the goal is simple: higher participation, and higher engagement, at every site, measured against where we started. And we'll get there the same way we got here: progress over perfection, one item at a time.